## Slide 1: सबकी योजना सबका विकास PEOPLE’S PLAN CAMPAIGN FOR GPDP
Maharashtra State
New Delhi, 11th September, 2018

## Slide 2: GPDP 2019-20
Govt. of Maharashtra has issued GPDP Guidelines for the Year 2019-20 (GR dt. 6 Sept. 2018)
Gram Sabha – 2nd Oct. to 31st Dec. 2018
Attendance & Presentation by All Dept. Functionaries in Gram Sabha

## Slide 3: GPDP 2019-20
GPDP Priorities - Basic Services &
Integration of :
  Poverty Eradication,
  Human, Social, Economic & Ecological
  Development,
  Public Service Delivery,
  Good Governance,
  Skill Development,
  Sustainable Development Goals (SDG)
  Sanitation, Liquid & Solid Waste Management

## Slide 4: GPDP 2019-20
Convergence of Gram Panchayat & SHGs
GPDP & Children below 18 yrs.
Aspirational Districts
Mission Antyodaya
GPDP in PESA GPs
No Cost / Low Cost Activities

## Slide 5: PEOPLE’S PLAN CAMPAIGN FOR GPDP
Detailed Instructions by Govt. vide letter dated 07th Sept. 2018
Sr. No. | Dept. / Office / Institute | Responsibility | Schedule
1 | RDD, GoM | Appointment of Nodal Officers in RDD Nodal Officers from State Dept. of 29 Subjects. Meeting of all State Depts. | Appointed 10th to 15th Sept ,2018

## Slide 6
Sr. No. | Dept. / Office / Institute | Responsibility | Schedule
2 | State Depts. Nodal Officers | Appointment of Functionaries for Special Gram Sabha Instructions to attend Gram Sabha as per schedule finalized by CEO Presentation in the Gram Sabha | 15th to 28th Sept, 2018 2nd Oct. to 31st Dec. 2018
3 | IT Cell, RDD, GoM | Nodal Officer for Uploading of Geo- Tagging Photos , Registration on Web Portal, Uploading Plans on Plan Plus | Appointed Oct. to Dec. 2018
4 | SPMU, RGSA | Nodal Officer for Campaign GPDP Guidelines Planning & Monitoring of Special Gram Sabha | Appointed Issued 2nd Oct. to 31st Dec. 2018

## Slide 7
Sr. No. | Dept. / Office / Institute | Responsibility | Schedule
5 | SIRD | Nodal Officer for CB&T Preparation of Training Modules for Facilitators, | 18th Sept.2018
6 | MSRLM | Nodal Officer for Mission Antyodaya, Appointment & Training of Facilitators Appointment of Facilitator for every GP Training of Facilitator Conduct & Monitoring of Base line Survey through Facilitator Coordinate Facilitators Activities with Gram Sabha Schedule finalized by CEO | Appointed 15th Sept, 2018 20 -25 Sept. 18 30th Sept 2018 Sept to Dec. 18

## Slide 8
Sr. No. | Dept. / Office / Institute | Responsibility | Schedule
7 | CEO, ZP | Monitor, Review & Implementation of Campaign Coordinate GPDP Guidelines and Campaign Activities Finalization of Special Gram Sabha Calendar (2nd Oct. to 31st Dec. 2018) Maximum 2 Gram Sabhas per day in a Block. Meeting of Dist. Level Officers of all State Depts. and ZP Appointment of Liaisoning Officers for Special Gram Sabha | Oct. to Dec. 2018 30th Sept, 18 25-30 Sept. 18 25-30 Sept. 18

## Slide 9
Sr. No. | Dept. / Office / Institute | Responsibility | Schedule
7 | CEO, ZP | Monitor appointment of Functionaries for every GP by all Line Depts. Display of Public Information Board Monitoring & Review of activities of facilitator, Line Dept. , Functionaries & finalization of GPDP. | 25 -30 Sept. 18 Before and After Special Gramsabha Oct. to Dec. 2018
8 | Divisional Commissioner | Monitor & Review of Implementation of the Campaign in the Division | Oct. to Dec. 2018