## Slide 1
People’s Plan Campaign
Sabki Yojana Sabka Vikas
2nd October – 31st December 2018

## Slide 2: ACTION PLAN : Assam

## Slide 3: Activity undertaken
Sl No | Activity | Action Taken
1 | Appointment of Nodal Officers for the campaign, baseline survey of Gram Panchayats (Mission Antyodaya) and Registration on web portal (www.gpdp.nic.in) | Appointed
2 | Appointment of facilitator for every Gram Panchayat/Rural Local body | Selected
3 | Training of Facilitators | Training Plan Scheduled
4 | Finalization of Gram Sabha wise calendar for holding of Gram Sabhas | Scheduled two Gram Sabhas
5 | Appointing frontline workers of all departments related to 29 subjects to be deputed for structured presentation in Gram Sabha meetings on the designated days | Letters sent to head of Line Departments.

## Slide 4: ACTION PLAN: Capacity building & TRAINING
Sno | Activity | Timeline
1 | Training | 
 | TOT for District Resource Person (DRP) | 10th September 2018- 13th September 2018
 | Training of Panchayat Level Facilitator (PLF) | 15th September 2018- 22nd September 2018
 | Training of Gaon Panchayat Secretaries | 18th September 2018 to 21st September 2018
 | Training of VCDC/VDC stateholder | 18th September 2018 to 21st September 2018
 | Training of Head of the Line Department at District level | 24th September 2018
 | ToT on preparation of Panchayat Poverty Reduction Plan for Master Trainers | 24th September 2018 to 6th October 2018
 | Training to SHGs members by Master Trainer for Panchayat Poverty Reduction Plan | 28th September 2018 to 28th October 2018
2 | Mission Antyodaya Survey | 20th September - 30th September 2018

## Slide 5: ACTION PLAN
Sno | Activity | 2nd October 2018 | 3rd Oct 2018 - 31st Oct 2018 | 1st Nov 2018- 20th Nov 2018 | 21st Nov 2018- 8th Dec 2018 | 8th Dec 2018- 31st Dec
1 | 1st Gram Sabha |  |  |  |  | 
2 | Gap identification and Preparation of Draft Plan |  |  |  |  | 
3 | 2nd Gram Sabha |  |  |  |  | 
4 | 3rd Gram Sabha |  |  |  |  | 
5 | Uploading of Plan in Planplus |  |  |  |  | 

## Slide 6: 1st GRAM SABHA
In this Gaon Sabha the following activities will be under taken:
    Data validation of Mission Antyodaya
    Review of current activities and fund utilization
    Approval of Annual Plan of FFC 2018 – 19

## Slide 7: Preparation of draft PLAN : 3rd Oct 2018 - 31st Oct 2018
Sitting at the Gaon Panchayat:
  Discussion on finding of the Mission Antyodaya data
  Identification of Gaps
  Discussion on the schemes of line department already implemented in the year 2018 – 19 and to be implemented by 2019 – 20.
  Discussion on the Perspective plan already prepared during Mi9ssion Mode (2017)
Preparation of Draft plan based on
  Gaps of Mission Antyodaya data
  Perspective Plan of last GPDP Mission Mode
  Schemes of line Department

## Slide 8: 2nd Gram sabha 1st Nov 2018- 20th Nov 2018
  Visioning and Prioritization Gaon Sabha
  Presentation of Line Departments
  Sharing of initiatives , schemes and services rendered by the line department.
  Share the the current year and for the coming year 2019 – 20 in the prescribed format
  Presentation of GP Poverty Reduction Plan by SHG

## Slide 9: 3rd Gram sabha 21st Nov 2018- 8th Dec 2018
  Gaon Sabha for Approval of GPDP for the year 2019-2020
    Approval of GPDP of the Annual Plan by the Gaon Sabha.

## Slide 10: Uploading of Plan in Planplus 8th Dec 2018- 31st Dec
  Uploading of approved Plan in PlanPlus.
  Annexure

## Slide 11: Thank you