Timeline for People’s Plan Campaign for Manipur

| Sl.No. | Activities | Timeline | Action By | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Meeting with MSRLM at SIRD Conference Room, Porompat | 12th Sept, 2018 | Discussion regarding SHG, Training Programme and Mission Antyodaya Application. | Deputy Director RD&PR, State level Officers of RD&PR and MSRLM, District level Officers of RD&PR. |
| 2 | Selection of facililators as Panchayat Secretary for Valley District and Village level Worker for Hill District | 13th Sept,2018 | Letter to Secretariat, Deputy Commissioner and BDOs | 16 Districts |
| 3 | Training of Facililators for Valley District | 14th to 18th Sept,2018 | District level Facililators | 161 Panchayat Secretaries |
| 4 | Training of Facililators for Hill District | 19th to 24th Sept,2018 | District level Facililators | 100 VLWs |
| 5 | Frontline appointment | 28th Sept,2018 | 16 Line Department | Pending from Line Department |
| 6 | Calendar for Special Sabha | 28th Sept,2018 | State level and District Level officers | pending |