## Slide 1
People’s Plan Campaign
Meghalaya
2nd October – 31st December 2018

## Slide 2: Activity
Sl No | Activity | Period / Action taken | Action taken by
1 | Appointment of State Nodal Officers for the campaign, | Appointed | Community and Rural Development Deptt
2 | Appointment of facilitator for every Gram Panchayat/ Village Council | Selected | NRLM Cell
3 | Training of Facilitators | 20th – 21st September 2018 26th -27th September 2018 | NRLM cell
4 | Mission Antyodaya data collection | 28th September 2018 | DRDA
5 | Confirmation of Mission Antyodaya data in Gram Sabha | 2nd October 2018 | SIRD/ NRLM/ DRDA

## Slide 3: Activity
Sl.no | Activity | Period | Action taken by
6 | Nomination of Frontline workers of all departments | 20th September 2018 | Concern Line Depts.
7 | Finalization of Calender for Special Gram Sabha | It is being coordinated | SIRD/ NRLM CELL/ MGNREGA CELL
8 | PRI-SHG convergence training | 25th September 2018 | SIRD/ NRLM cell
9 | Public Information Board installation in all GP/VECs | 2nd October 2018 | BDOs
10 | Workshop with all line departments under RGSA and GPDP | Conducted on 6th & 11th September 2018 | SIRD
11 | Total no. Of villages in Meghalaya | 6026 (VECs are in place) (6839) | 
12 | Registration on web portal | Not done | SIRD/ C& RD Deptt

## Slide 4: ACTION PLAN: Capacity building & TRAINING
Sno | Activity | Timeline
1 | Training | 
 | TOT for District Resource Person (DRP) | Decision not taken
 | Training of Facilitator in 27intensive NRLM blocks out of 46 blocks | 20th – 21st September 2018 26th - 27th September 2018
 | Training of Secretaries of VEC /Gramsabhas | 2nd October – 1st November 2018
 | Training of VEC stateholder | 18th September 2018 to 21st September 2018
 | Training of Head of the Line Department at District level | 24th September 2018
 | ToT on preparation of Panchayat Poverty Reduction Plan for Master Trainers | 25th September 2018 to 6th October 2018
 | Training to SHGs members by Master Trainer for Panchayat Poverty Reduction Plan | 30th September 2018 to30th October 2018
2 | Mission Antyodaya Survey | 28 September 2018

## Slide 5: ACTION PLAN
Sno | Activity | 2nd October 2018 | 3rd Oct 2018 - 31st Oct 2018 | 1st Nov 2018- 30th Nov 2018 | 1st Dec – 15th Dec 2018 | 16th Dec 2018- 31st Dec
1 | 1st Gram Sabha |  |  |  |  | 
2 | Gap identification and Preparation of Draft Plan |  |  |  |  | 
3 | 2nd Gram Sabha |  |  |  |  | 
4 | 3rd Gram Sabha |  |  |  |  | 
5 | Uploading of Plan in Planplus |  |  |  |  | 

## Slide 6: ISSUES
1 GP = 1 Village. There is a need of preparing VDP for each village
Issue of local self governance

## Slide 7: 1st GRAM SABHA
In this Gram Sabha the following activities will be under taken:
    Data validation of Mission Antyodaya
    Review of current activities and fund utilization
    Annual Plan of FFC to be followed

## Slide 8: Preparation of draft PLAN : 3rd Oct 2018 - 31st Oct 2018
Sitting at the GP/ VC:
  Discussion on finding of the Mission Antyodaya data
  Identification of Gaps
  Discussion on the schemes of line department already implemented in the year 2018 – 19 and to be implemented by 2019 – 20.
  Discussion on the Perspective plan already prepared during Mi9ssion Mode (2017)
Preparation of Draft plan based on
  Gaps of Mission Antyodaya data
  Perspective Plan of last VDP Mission Mode
  Schemes of line Department

## Slide 9: 2nd Gram sabha 1st Nov 2018- 30th Nov 2018
  Visioning and Prioritization Gram Sabha
  Presentation of Line Departments
  Sharing of initiatives , schemes and services rendered by the line department.
  Share the the current year and for the coming year 2019 – 20 in the prescribed format
  Presentation of Village Poverty Reduction Plan by SHG

## Slide 10: 3rd Gram sabha 1st Dec- 15th Dec 2018
  Gram Sabha for Approval of VDP for the year 2019-2020
    Approval of VDP of the Annual Plan by the Gram Sabha.

## Slide 11: Uploading of Plan in Planplus 16th Dec 2018- 31st Dec
  Uploading of approved Plan in PlanPlus.

## Slide 12: Thank you