## Slide 1: DRAFT People’s Plan Campaign Sabki Yojana Sabka Vikas 2nd October – 31st December 2018 MIZORAM

## Slide 2
ACTIONS TAKEN
Training on GPDP for ERs (VCs)
Appointment of State Nodal Officer
579 Facilitators are Selected from SHGs. (in addition, BFT and FI & AFI of LAD Dept. could be identified)
Facilitation of preparation of GPDP/VDP for two villages of Reiek RD Block
Draft Guidelines for GPDP/VDP is in the Planning Department for approval.
The Mizoram Local Government (Panchayat) Act, 2018 is in a draft stage to be approved by Mizoram State Legislative Assembly.

## Slide 3
Action to be taken
State Level Meeting on People’s Plan Campaign to be held on 20th September, 2018.
Approval and additional appointment of Facilitators
Training programmes for Facilitators :
Appointment of District Nodal officers
Collection of Mission Antyodaya data.
Confirmation of collected Mission Antyodaya data by Gram Sabha
Nomination of Frontline Workers of all department related to 29 subjects in XI schedule to be deputed for structured presentation in Gram Sabha.
Conducting Special Gram Sabha for GPDP :
Training on PRI-SHG Convergence.
Display of Public Information Board in every Gram Panchayat and uploading of geo-tagged photographs of it on the web portal (www.gpdp.nic.in)

## Slide 4: ACTION PLAN - I
Sl. No | Activity | 20th Sep, 2018 | 2nd Week of October, 2018 | 3rd Week of October, 2018 | 4th Week of October, 2018 | 1st Week of November
1 | State Level Meeting |  |  |  |  | 
2 | Approval of Facilitators |  |  |  |  | 
3 | Nomination of Frontline Workers |  |  |  |  | 
4 | Training of Facilitators |  |  |  |  | 
5 | Training on PRI-SHG Convergence |  |  |  |  | 

## Slide 5: ACTION PLAN - II
Sl. No. | Activity | 2nd Oct, 2018 | October, 2018 | 1st to 3rd Wk of Nov | 4th Wk of Nov to 1st wk of Dec | 2nd and 3rd Wk of Dec
1 | 1st Gram Sabha |  |  |  |  | 
2 | Collection of M.A. Data |  |  |  |  | 
3 | Gap identification and Preparation of Draft Plan |  |  |  |  | 
4 | 2nd Gram Sabha |  |  |  |  | 
5 | 3rd Gram Sabha |  |  |  |  | 
6 | Display of Public Information Board & Uploading of Plan in Planplus |  |  |  |  |