Timeline for People’s Plan Campaign for Arunachal Pradesh (w.e.f 2nd Oct – 31st Dec’2018).

| Sl No | Activities / item of work | Timeline | Action By | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Training to the District level Trainers/ Resource Persons on People’s Plan Campaign (2 Days by SIRD&PR, Department of PR ,RD and ArSRLM) | 13-14 Sept’2018 | SIRD&PR, Arunachal Pradesh & PR Department/RD/Ar. SRLM | 67 nos. of Panchayati Raj staff trained. |
| 02 | Video Conferencing to all the Deputy Commissioners by Chief Secretary in the presence of Secretary (RD&PR) & Director (PR) | 14th Sept’2018 | Chief Secretary / Secretary (PR) / Director (PR) | Interfaced |
| 03 | Selection / appointment of Gram Panchayat Facilitators | By 19th Sept’2018 | DCs / DPDOs | Instructions issued. |
| 04 | Selection / appointment of Frontline workers | By 28th Sept’2018 | HoDs / District Level HoDs | Meeting fixed on 20th September 2018 by CS with all Secretaries. |
| 05 | Training to Gram Panchayat Facilitators in Districts and Chairperson of Interim Committee / Member Secretaries for collection of Data as per Mission Antyodaya (MA) parameters and on comprehensive GPDP Preparation. | 21st Sept – 26th Sept’2018 | District Level Facilitators and SIRD&PR Faculties. | Dates of training will be finalized on receipt of list from Districts. |
| 06 | Training to Block Level MA Parameter to Block level functionaries on data uploading | 21st Sept – 26th Sept’2018 | SIRD&PR, MIS team (PR, RD, SIRD&PR, ArSRLM) | Training will be conducted in SIRD&PR. |
| 07 | Collection of Data in Mission Antyodaya Parameters by GP Facilitators (PTA/CCAA/CA/ GRGS/Ar. SRLM/ CRP/VRPs) | 23rd - 28th Sept’2018 | GP Facilitators | From HQ(SIRD&PR Faculties ,PR Officers/RD/ArSRLM)/ Officers from HQ (District wise division) |
| 08 | Installation of Public Information Board (PIB) in each GP | 23rd – 30th Sept 2018 | DC / DPDO / Chairperson of Gram Panchayat Interim Committees. |  |
| 09 | Data uploading in MA Apps Draft hard copy print out ready for 2nd Oct (First Gram Sabha) | 24th -30th Sept’2018 | MIS Block level functionaries / GP Facilitators |  |
| 10 | Finalizations of Gram Sabha Calendar | 25th -30th Sept’2018 | Deputy Commissioners / DPDOs / Member Secretaries | DCs will finalize the Gram Sabha schedule in such a way that the Chairperson and Member Secretaries preside all Gram Sabhas of his/her administrative jurisdiction except first Gram Sabha on 2nd October 2018 for which the chairperson shall delegate one of his competent member to preside. |
| 11 | Awareness Campaign /Pada Yatra / slogan / door to door Campaign Pamphlet / Poster / Chart Paper / Wall Writing / Invitations for 2nd October Gram Sabha. | 30th Sept/ 1st Oct’2018 in each Gram Panchayat | MS/GB/Anganwadi Workers/Asha/AFA/VFA/HFA/FD/Teachers/PR Functionaries /GBs/ CA/CCA/PTA/GRS/VRPs/ GP Facilitators/CRPs |  |
| 12 | Conduct of first Gram Sabha (GS) for validation of Mission Antyodaya Data. | 2nd Oct’2018 | Gram Panchayat Chairpersons of Interim Committees / GP Facilitators / Members Secretaries and Frontline workers. | The GSs starting from 2nd Oct 2018. |
| 13 | Conduct of Second Gram Sabha and presentation of draft GPDP. | 3rd Oct- 5th Nov’2018 | Gram Panchayat Chairpersons of Interim Committees/ GP Facilitators/ Members Secretaries and Frontline workers. | Final Calendar to all Gram Panchayats of the District will be decided by the DC. |
| 14 | Conduct of third & final Gram Sabha and vetting of GPDP for 2019-20 and approval of minutes by GP Chairperson. | 6th Nov – 10th Dec’2018 | Gram Panchayat Chairpersons of Interim Committees/ GP Facilitators/ Members Secretaries and Frontline workers. | Dates will be finalized by DC concerned. |
| 15 | Uploading of GPDP Plan for 2019-20 | By 20th Dec’2018 | By DPDOs / SNO |  |

(Repo Ronya)

Director (PR)

Govt. of Arunachal Pradesh

Itanagar.